| February 2007 | March | April | May |
| --- | --- | --- | --- |
| Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training |
| Week 1 Preparatory week Contact partners Meeting trainers Check up materials Advertisement of project | Week 5 Training Introduction Getting to know the group Methodology Evening activity: Screening of documentary/fiction | Week 9 Training Basics Evening activity: Screening of documentary/fiction | Week 13 Training Advanced Techniques Evaluation of first assignment Evening activity: Screening of documentary/fiction |
| Week 2 Preparatory week Idem | Week 6 Training Basics How to use the camera | Week 10 Training Basics First assignment | Week 14 Training Advanced Techniques |
| Week 3 Prep week Advertisement of the project in media and schools Day of presentation at the centre Selection of team Appeal to professionals | Week 7 Training Basics | Week 11 Training Basics of editing Deconstruction of a news features- screening followed by discussion | Week 15 Training Advanced Techniques Light Second Assignment |
| Week 4 Prep Week Selection of participants 1 day for adults 1 day for youth. Selection based on motivation, short interviews with candidates. Monthly meeting of the team | Week 8 Training Basics Deconstruction of a documentary film (screening and discussion) Monthly meeting of the team | Week 12 Training Basics of editing Look at the first assignment Monthly meeting of the team | Week 16 Training Advanced Techniques Sound- including types of microphone, their proper use, and monitoring levels Evaluation with the groups Monthly meeting of the team Evaluation |
| June 2007 | July | August | September |
| Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training | Phase 1 Setting up of the project and training |
| Week 17 Training Advanced Technics Look at the Second Assignment Workshop with Professionals (for instance a cameraman for a press agency) Practical shooting -Session in outside conditions/fieldtrip Evening activity: Screening of documentary/fiction | Week 21 Training Advanced Technics Editing Presentation of the scripts of personal project. Evening activity: Screening of documentary/fiction | Week 25 Work on personal projects Follow-up with trainers Evening activity: Screening of documentary/fiction | Week 29 Training Advanced Technics Subject according group’s evaluation Group activity: a group to follow the French theatre companies tour. Evening activity: Screening of documentary/fiction |
| Week 18 Training Advanced Techniques Workshop script writing- Evaluation of second Assignment Proposal to publish/ publicize assignment on website | Week 22 Training Advanced Techniques Editing Workshop with professionals- Filming Fiction | Week 26 Training Advanced Workshop with professionals- working with Television | Week 30 Training Advanced Techniques Subject according group’s evaluation Screening of personal projects following by discussion and critics Selection of trainers |
| Week 19 Training Advanced techniques Workshop: conducting an interview and research/ Gender- sensitivity Third Assignment (bigger personal project to present with script writing) Can be group project (no more than 3 persons/ group) | Week 23 Training Advanced Techniques Editing Follow-up with personal projects | Week 27 Training Advanced Workshop with professionals Follow up with projects | Week 31 Advanced Techniques Subject according group’s evaluation ¨Finalization of personal projects |
| Week 20 Training Advanced techniques Editing Proposals for summer camps (filming activities, conducting workshops; etc.) Monthly meeting of the team- Evaluation | Week 24 Training Advanced techniques Editing Workshop with professionals/ presentation of art studies in Palestine Monthly meeting of the team | Week 28 Training Advanced Follow up with projects Projection of the footage and suggestions Group evaluation: for the last month of training – what can be done? What needs to be look at again? Announcement for junior trainers/technical assistants Monthly meeting | Week 32 Final evaluation Screening of personal projects Evening activity: Screening of the personal projects to the community; invitation via media. Monthly meeting evaluation of phase 1 |
| October 2007 | November | December | January 2008 |
| Phase 2 Development of visual creations | Phase 2 Development of visual creations | Phase 2 Development of visual creations | Phase 2 Development of visual creations |
| Week 29 Brainstorming with the group and trainers about ideas of visual creations. What do we have so far? What do we want to create? Presentation of previous projects/ products from others to get ideas. Organisation of small groups Proposal of a photoclub/videoclub Evening activity: Screening of documentary/fiction | Week 33 Development of the ideas Writing of proposals Evening activity: Screening of documentary/fiction | Week 37 Finalization of the ideas/proposals Selection of previous materials that can be used Evening activity: Screening of documentary/fiction | Week 41 Listing of the materials for the realization of the ideas Evening activity: Screening of documentary/fiction |
| Week 30 Preparation of proposals- Each group work on developing an idea Communication/ listing of relevant institutions/ festivals/ partners (ongoing activity for this phase) Communication – brainstorming- what can be proposed as services to companies/ organisations? Group tasks to elaborate strategies and materials | Week 34 Development of the ideas Writing of proposals | Week 38 Finalization of the ideas/proposals Selection of previous materials that can be used | Week 42 Final decision concerning the proposals (what is really feasible) with the agreement of the group/ team Gathering/ purchase of materials necessary for the realization of the ideas/ concepts |
| Week 31 Presentation of the ideas/ concepts developed by the groups Critical analysis and suggestions to improve Selection of the ideas | Week 35 Presentation of the ideas to a panel of external experts. Sending of the ideas/concepts/proposals to a certain number of experts | Week 39 Finalization of the ideas/proposals Selection of previous materials that can be used | Week 43 Gathering/ purchase of materials necessary for the realization of the ideas/ concepts |
| Week 32 Development of the ideas Writing of proposals Monthly meeting of the team | Week 36 Discussion on the comments/ advice given by experts Monthly meeting of the team | Week 40 Meeting/ workshop with professionals Monthly meeting of the team | Week 44 Presentation of the concepts to partners/ groups/ etc. Monthly meeting of the team- Evaluation of phase 2 |
| February 2008 | March | April | May |
| Phase 3 Finalization and production | Phase 3 Finalization and production | Phase 3 Finalization and production | Phase 3 Finalization and production |
| Week 45 Brainstorming about the finalization Timetable and group organization Specification of the tasks List of partners and experts needed (printers, producers, distributors, translators, etc.) Review budget for realization and production. Evening activity: Screening of documentary/fiction | Week 49 Finalization of the visuals Contacts with partners for production- selection of printers/ producers Evening activity: Screening of documentary/fiction | Week 53 Finalization of the visuals- Editing Evening activity: Screening of documentary/fiction | Week 57 Communication- realization of advertisement materials (short written presentation, post on websites, teasers for films, etc.) Production Evening activity: Screening of documentary/fiction |
| Week 46 Meeting with external experts and professionals Checking of materials | Week 50 Finalization of the visuals | Week 54 Finalization of the visuals- Editing Screening of the footage to groups and external experts for last suggestions/ comments | Week 58 Communication Production |
| Week 47 Finalization of the visuals (shooting of additional footage/ interviews/ etc.) | Week 51 Finalization of the visuals | Week 55 Final editing taken into account comments | Week 59 Communication Production Follow-up with the professionals. Checking of one copy |
| Week 48 Finalization of the visuals Monthly meeting of the team Evaluation project after 1 year (writing of a report to be presented to all partners) Re-evaluation of budget Evaluation of role of team members | Week 52 Finalization of the visuals- Editing Monthly meeting of the team | Week 56 Final version screened. Then all materials given to producers/ printers, etc. Communication: listing of relevant events in the summer. Check the deadlines and application forms Monthly meeting of the team | Week 60 Communication Production – check up with the stocks. Monthly meeting of the team Evaluation of phase 3 |
| June 2008 | July | August | September |
| Phase 4 Diffusion | Phase 4 Diffusion | Phase 4 Diffusion | Phase 4 Diffusion |
| Week 61 Brainstorming about strategies of communication/ diffusion/ ideas: distribution networks; diffusion on line, etc. Calendars Tasks assignments- Listing of possible events and opportunities (photo tour, summer festivals, etc.) Participation to summer camps? Contact with partners (ongoing) and advertisement on websites both at local and international level Evaluation of action/ needs of video and photo clubs Evening activity: Screening of documentary/fiction | Week 65 Communication Participation/ organisation of events Diffusion of products Evening activity: Screening of documentary/fiction | Week 69 Communication Participation/ organisation of events Diffusion of products Evening activity: Screening of documentary/fiction | Week 73 Communication Participation/ organisation of events Diffusion of products Brainstorming 1: what to do next? New project? If yes, identification of relevant funding opportunities for 2009 and task assignment Evening activity: Screening of documentary/fiction |
| Week 62 Presentation of the events/ calendar Events in the camp: invitation to experts and public to see the visuals (screenings) Meeting with experts/ professionals to test the visuals and brainstorm about distribution | Week 66 Communication Participation/ organisation of events Diffusion of products | Week 70 Communication Participation/ organisation of events Diffusion of products | Week 74 Communication Participation/ organisation of events Diffusion of products |
| Week 63 Applications for participation to festivals/ events Review of budget according to the participation of events | Week 67 Communication Participation/ organisation of events Diffusion of products | Week 71 Communication Participation/ organisation of events Diffusion of products | Week 75 Communication Participation/ organisation of events Diffusion of products |
| Week 64 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team | Week 68 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team | Week 72 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team | Week 76 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team Evaluation |
| October 2008 | November | December | January 2009 |
| Phase 4 Diffusion | Phase 4 Diffusion | Phase 4 Diffusion | Phase 4 Diffusion |
| Week 74 Communication Participation/ organisation of events Diffusion of products Follow up with next project Evening activity: Screening of documentary/fiction | Week 78 Communication Participation/ organisation of events Diffusion of products Evening activity: Screening of documentary/fiction | Week 82 Communication Participation/ organisation of events Diffusion of products Evening activity: Screening of documentary/fiction | Week 86 Communication Participation/ organisation of events Diffusion of products Brainstorming 2: what to do next? New project? What remains to be done during the last month? Evening activity: Screening of documentary/fiction |
| Week 75 Communication Participation/ organisation of events Diffusion of products | Week 79 Communication Participation/ organisation of events Diffusion of products | Week 83 Communication Participation/ organisation of events Diffusion of products | Week 87 Communication Participation/ organisation of events Diffusion of products |
| Week 76 Communication Participation/ organisation of events Diffusion of products | Week 80 Communication Participation/ organisation of events Diffusion of products | Week 84 Communication Participation/ organisation of events Diffusion of products | Week 88 Finalization of the final report Elaboration of a press book |
| Week 77 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team | Week 81 Communication Participation/ organisation of events Diffusion of products Monthly meeting of the team | Week 85 Communication Participation/ organisation of events Diffusion of products Preparation of final report Monthly meeting of the team | Week 89 Presentation of final report to partners. Monthly meeting of the team Final evaluation |